## Sources and Uses of Funds
AFRICA CENTER OF EXCELLENCE FOR TRAINING SEED SCIENTISTS & TECHNOLOGISTS
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
Statement of Sources and Uses of Funds
for the semi-annual period ending June 2019
Cummulative for
Sources of Fund | Semi-Annual Period ending June 2019 | Financial Year End June 2019
Opening Cash Balance 01.01.2019 | 277753
Government Funds | 0 | 0
World Bank IDA Funds | 0 | 0
Others |  | 0
Total | 277753 | 0
Add Receipts
Government Funds | 322878.23 | 608895.18
World Bank IDA Funds | 550000 | 6248404.38
Others (Exchange Gain) | 0 | 1170
Total Financing | 1150631.23 | 6858469.56
Less: ACE Expenditure
1.0 - Set-up Institutional Framework for Commencement of ACE | 682.6 | 6106.75
2.0 - Strengthen Education Capacity | 57868.43 | 857787.29
3.0 - Strengthen Education Capacity & Development Impact | 115465.89 | 702658.07
4.0 - Strengthen Research Capacity (Excellence) | 434838.29 | 4720934.42
5.0 - Strengthen Education & Research Capacity (Fin. Sustainability) | 0 | 0
6.0 - Strengthen Education & Research Capacity | 10565.93 | 31890.12
7.0 - Adhere to Best Financial Management Practices | 4815.03 | 36507.22
8.0 - Undertake Best Procurement Practices | 0 | 3439.78
9.0 - Contingency | 3453.84 | 19141.14
Total Uses of Funds by Components | 627690.01 | 6335521.52
Closing Balances | 522941.22 | 522948.04
Government Funds
World Bank IDA Funds
Others
Total Closing Cash Balance | 522941.22 | 522948.04
Signed by:
Centre Leader:…………………………
Professor Eric Danquah

## uses of fund by component
AFRICA CENTER OF EXCELLENCE FOR TRAINING SEED SCIENTISTS & TECHNOLOGISTS
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds (Breakdown)
for the semi-annual period ending June 2019
(USD)
Expenditure | Semi-Annual Period ending June 2019 |  |  | Cummulative for |  |  | Explanation of | PAD /Life of | Revised
[5 empty] | Financial Year End December 2019 |  | Variance | Project | PAD
| Actual | Planned | Variance | Actual | Planned | Variance
1.0 Set-up Institutional Framework for Commencement of Ace
1.1 Negotiate and sign funding contract |  |  |  | 0 | 500
1.2 Governance Framework in Place | 0 | 0 | 0 | 0 | 1000
1.3 Schedule Hold ACE Implementation Meetings | 682.6 | 1000 | 317.4 | 6106.75 | 9000 | 2893.25
1.4 Collect, Collate and Analyse Data for M&E | 0 | 250 | 250 | 0 | 1500 | 1500
1.5 Schedule and Hold ACE M&E Meetings | 0 | 250 | 250 | 0 | 75000 | 75000
Sub Total | 682.6 | 1500 | 817.4 | 6106.75 | 87000 | 79393.25 | Note 1 | 4 Years
2.0 Strengthen Education Capacity
2.1 Develop Mphil SST curicullum |  |  | 0 |  | 9525 | 9525
2.2 Obtain programme accreditation | 0 | 0 | 0 | 50711.04 | 50000 | -711.04
2.3 Admit Quality Students into PhD Programme | 25543.97 | 45900 | 20356.03 | 391554.66 | 467735 | 76180.34
2.4 Admit Quality Students into Mphil SST Programme | 9652.25 | 44500 | 34847.75 | 240879.26 | 347930 | 107050.74
2.5 Register Continuing Students | 0 | 60000 | 60000 | 0 | 122750 | 122750
2.6 Offer required taught courses to first year PhD and Mphil SST students | 13352 | 34500 | 21148 | 109019.82 | 157200 | 48180.18
2.7 Organise training workshops and serminars for students' learning | 0 | 20000 | 20000 | 0 | 132960 | 132960
2.8 Attract, retain and retool faculty in ACE relevant areas | 8520.21 | 32500 | 23979.79 | 25560.51 | 216000 | 190439.49
2.9 Students Stipends | 800 | 0 | -800 | 36462 | 24000 | -12462
2.10 Students Laptops & External Drives | 0 |  |  | 3000 | 3000 | 0
2.11 Students Book Allowance | 0 |  |  | 600 | 600 | 0
Sub Total | 57868.43 | 237400 | 179531.57 | 857787.29 | 1531700 | 673912.71 | Note 2 | 4 Years
3.0 Strengthen Education Capacity & Development Impact
3.1 Broaden students' knowledge through exposure to advanced institutions | 1931.26 | 40000 | 38068.74 | 7411.11 | 331500 | 324088.89
3.2 Engage the NARs in Africa and CG Centres for students' research | 0 | 40000 | 40000 | 0 | 363320 | 363320
3.3 Engage Seed Companies for students' internship | 0 | 25000 | 25000 | 0 | 67200 | 67200
3.4 Engage partners from advanced institutions for teaching and learning | 59158.85 | 60000 | 841.15 | 146922.5 | 78000 | -68922.5
3.5 Engage LCIC in Ghana to scale up the maize hybrid commercialization |  | 100000 | 100000 | 0 | 127700 | 127700
3.6 ACE Workshops and Management/Staff Travel | 48137.24 | 49000 | 862.76 | 119404.32 | 127700 | 8295.68
3.7 Workshops/Serminars - Short Courses | 6238.54 | 55000 | 48761.46 | 428920.14 | 420000 | -8920.14
Sub Total | 115465.89 | 369000 | 253534.11 | 702658.07 | 1515420 | 812761.93 | Note 2 | 4 Years
4.0 Strengthen research capacity (excellence)
4.1 WACCI model farm upgrade | 16504.21 | 50000 | 33495.79 | 475007.88 | 450000 | -25007.88
4.2 New Lecture Rooms, Seed Science Laboratory and Bioinformatics Platform | 237948.36 | 225000 | -12948.36 | 2322980.02 | 2000000 | -322980.02
4.3 Students' supervisory committees and research supervision | 0 | 1250 | 1250 | 0 | 63350 | 63350
4.4 4 X 4 cross country SUV for research supervision | 0 | 0 |  | 115350.83 | 100042 | -15308.83
4.5 Peer-reviewed journals and publication | 160.42 | 4500 | 4339.58 | 1735.81 | 26000 | 24264.19
4.6 Students' research | 133745.27 | 213324.8 | 79579.53 | 783353.08 | 1174812 | 391458.92
4.7 Seed Science Laboratory Equipment | 0 | 0 | 0 | 231420.36 | 232000 | 579.64
4.8 Bioinformatics Equipment & Accessories | 0 | 0 | 0 | 295311.76 | 265000 | -30311.76
4.9 Conference/Meeting room Equipment | 0 | 0 | 0 | 0 | 90000 | 90000
4.10 Tissue Culture/Cold room Equipment & Accessories | 11493.59 | 22000 | 10506.41 | 11493.59 | 103835 | 92341.41
4.11 33-seator bus students' travel | 0 | 0 | 0 | 87704.64 | 93042 | 5337.36
4.12 Accounting database and maintenance | 0 | 5500 | 5500 | 10716.68 | 11000 | 283.32
4.13 Network Equipment & Accessories | 110.7 | 0 | -110.7 | 11847.11 | 21000 | 9152.89
4.14 Computers and Accessories | 110.71 | 0 | -110.71 | 25432.95 | 25000 | -432.95
4.15 General Office Consumables | 11626.38 | 6000 | -5626.38 | 62048.58 | 55000 | -7048.58
4.15 Lecture Room Equipment & Accessories | 0 | 0 | 0 | 5108.73 | 6500 | 1391.27
4.16 Vehicle Running Costs | 21056.86 | 19000 | -2056.86 | 77055.67 | 65000 | -12055.67
4.17 Office Furniture & Fittings | 2081.79 | 2500 | 418.21 | 59412.87 | 65000 | 5587.13
4.18 Students' Accommodation | 0 | 0 | 0 | 141000.88 | 78500 | -62500.88
4.19 Medical Insurance & Aid | 0 | 0 | 0 | 3952.98 | 4500 | 547.02
Sub Total | 434838.29 | 549074.8 | 114236.51 | 4720934.42 | 4929581 | 208646.58 | Note 2 | 4 Years
5.0 Strengthen education and research capacity (financial sustainability)
5.1 Raise revenue from external sources (full cost fees payment - Sponsors & Donors) |  | 0 | 0 | 0 | 0 | 0
5.2 Raise revenue from external sources (commercialization and tech. marketing) |  |  |  |  | 0
5.3 Raise revenue from external sources (short term training) |  |  |  |  | 0
5.4 Raise revenue from external sources (consultancy services) |  |  |  |  | 0
5.5 Raise revenue from external sources (fees from greenhouse facilities & labs) |  |  |  |  | 0
5.6 Raise revenue from external sources (rent from facilities hiring) |  |  |  |  | 0
5.7 Raise revenue from external sources (endowment funds establishment) |  |  |  |  | 0
5.8 Raise revenue from external sources (contract research overheads) |  |  |  |  | 0
0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0
6.0 Strengthen education and research capacity
6.1 Provide and maintain academic infrastructure/T & R facilities | 10565.93 | 7500 | -3065.93 | 31890.12 | 71120.29 | 39230.17
Sub Total | 10565.93 | 7500 | -3065.93 | 31890.12 | 71120.29 | 39230.17 | Note 2
7.0 Adhere to best Financial Management Practices
7.1 Prepare and submit annual financial reports |  | 0 | 0 | 0 | 0 | 0
7.2 Ensure transparency in financial management (web-access to reports) |  | 0 | 0 | 0 | 0 | 0
7.3 Ensure internal & external audit oversight | 4815.03 | 16000 | 11184.97 | 36507.22 | 55000 | 18492.78
7.4 Ensure complete retirement of funds advanced for students' research |  | 0 | 0 | 0 | 0 | 0
Sub Total | 4815.03 | 16000 | 11184.97 | 36507.22 | 55000 | 18492.78
8.0 Undertake best procurement practices
8.1 Undertake third-party procurement processes verification | 0 | 16000 | 16000 | 3439.78 | 31000 | 27560.22
8.1 Ensure timeliness of procurement process | 0 | 0 | 0 |  | 0 | 0
Sub Total | 0 | 16000 | 16000 | 3439.78 | 31000 | 27560.22
Gain/Loss on Revaluation |  |  |  | -42943.27
Contingency | 3453.84 | 6000 | 2546.16 | 19141.14 | 100000 | 80858.86 | Note 3
Grand Total Uses of Funds | 627690.01 | 1202474.8 | 574784.79 | 6335521.52 | 8320821.29 | 1940856.5
Signed by:………………………
Prof. Eric Danquah
(Centre Leader)
Highlights for DLR 2.8
DLR 2.8.1 - New building construction | 0
DLR 2.8.2 - Laboratory equipment
DLR 2.8.3 - WACCI farm upgrade
DLR 2.8.4 - New building completion

## notes
AFRICA CENTER OF EXCELLENCE FOR TRAINING SEED SCIENTISTS & TECHNOLOGISTS
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED | AMOUNT DISBURSED | UNDISBURSED BALANCE
1.0 Set-up Institutional Framework for Commencement of Ace

## Sheet2
Desription | Amount (USD) | % of Award (USD)
Grant Budget (Award) | 8000000 | 100%
Cumulative Disbursement | 6248404.38 | 78.11%
Cumulative Expenditure | 6335521.52 | 79.19%