## Sources and Uses of Funds
AFRICA CENTER OF EXCELLENCE FOR TRAINING SEED SCIENTISTS & TECHNOLOGISTS
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
Statement of Sources and Uses of Funds
for the semi-annual period ending December 2019
Cummulative for
Sources of Fund | Semi-Annual Period ending December 2019 | Financial Year End December 2019
Opening Cash Balance 01.01.2019 | 277753
Government Funds | 0 | 0
World Bank IDA Funds | 0 | 0
Others |  | 0
Total | 277753 | 0
Add Receipts
Government Funds | 0 | 608895.18
World Bank IDA Funds | 351658.18 | 6600062.56
Others (Exchange Gain) | 0 | 1170
Total Financing | 629411.18 | 7210127.74
Less: ACE Expenditure
1.0 - Set-up Institutional Framework for Commencement of ACE | 618.95 | 6725.7
2.0 - Strengthen Education Capacity | 143321.99 | 1001109.28
3.0 - Strengthen Education Capacity & Development Impact | 96301.24 | 798959.31
4.0 - Strengthen Research Capacity (Excellence) | 253337.09 | 4974271.51
5.0 - Strengthen Education & Research Capacity (Fin. Sustainability) | 0 | 0
6.0 - Strengthen Education & Research Capacity | 169238.42 | 201128.54
7.0 - Adhere to Best Financial Management Practices | 4746.85 | 41254.07
8.0 - Undertake Best Procurement Practices | 10025.2 | 13464.98
9.0 - Contingency | 1864.31 | 21005.45
Total Uses of Funds by Components | 679454.05 | 7014975.57
Closing Balances | -50042.87 | 195152.17
Government Funds
World Bank IDA Funds
Others
Total Closing Cash Balance | -50042.87 | 195152.17
Signed by:
Centre Leader:…………………………
Professor Eric Danquah

## uses of fund by component
AFRICA CENTER OF EXCELLENCE FOR TRAINING SEED SCIENTISTS & TECHNOLOGISTS
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds (Breakdown)
for the semi-annual period ending December 2019
(USD)
Expenditure | Semi-Annual Period ending December 2019 |  |  | Cummulative for |  |  | Explanation of | PAD /Life of | Revised
[5 empty] | Financial Year End December 2019 |  | Variance | Project | PAD
| Actual | Planned | Variance | Actual | Planned | Variance
1.0 Set-up Institutional Framework for Commencement of Ace
1.1 Negotiate and sign funding contract |  |  |  | 0 | 500
1.2 Governance Framework in Place | 0 | 0 | 0 | 0 | 1000
1.3 Schedule Hold ACE Implementation Meetings | 618.95 | 1000 | 381.05 | 6725.7 | 9000 | 2274.3
1.4 Collect, Collate and Analyse Data for M&E | 0 | 250 | 250 | 0 | 1500 | 1500
1.5 Schedule and Hold ACE M&E Meetings | 0 | 250 | 250 | 0 | 75000 | 75000
Sub Total | 618.95 | 1500 | 881.05 | 6725.7 | 87000 | 78774.3 | Note 1 | 4 Years
2.0 Strengthen Education Capacity
2.1 Develop Mphil SST curicullum | 2000 |  | -2000 | 2000 | 9525 | 7525
2.2 Obtain programme accreditation | 0 | 0 | 0 | 50711.04 | 50000 | -711.04
2.3 Admit Quality Students into PhD Programme | 65007.59 | 67000 | 1992.41 | 456562.25 | 467735 | 11172.75
2.4 Admit Quality Students into Mphil SST Programme | 26620.17 | 44500 | 17879.83 | 267499.43 | 347930 | 80430.57
2.5 Register Continuing Students | 0 | 60000 | 60000 | 0 | 122750 | 122750
2.6 Offer required taught courses to first year PhD and Mphil SST students | 28920.98 | 34500 | 5579.02 | 137940.8 | 157200 | 19259.2
2.7 Organise training workshops and serminars for students' learning | 0 | 20000 | 20000 | 0 | 132960 | 132960
2.8 Attract, retain and retool faculty in ACE relevant areas | 17798.25 | 32500 | 14701.75 | 43358.76 | 216000 | 172641.24
2.9 Students Stipends | 2975 | 0 | -2975 | 39437 | 24000 | -15437
2.10 Students Laptops & External Drives | 0 |  |  | 3000 | 3000 | 0
2.11 Students Book Allowance | 0 |  |  | 600 | 600 | 0
Sub Total | 143321.99 | 258500 | 115178.01 | 1001109.28 | 1531700 | 530590.72 | Note 2 | 4 Years
3.0 Strengthen Education Capacity & Development Impact
3.1 Broaden students' knowledge through exposure to advanced institutions | 0 | 40000 | 40000 | 7411.11 | 331500 | 324088.89
3.2 Engage the NARs in Africa and CG Centres for students' research | 0 | 40000 | 40000 | 0 | 363320 | 363320
3.3 Engage Seed Companies for students' internship | 0 | 25000 | 25000 | 0 | 67200 | 67200
3.4 Engage partners from advanced institutions for teaching and learning | 46299.78 | 60000 | 13700.22 | 193222.28 | 122000 | -71222.28
3.5 Engage LCIC in Ghana to scale up the maize hybrid commercialization |  | 100000 | 100000 | 0 | 127700 | 127700
3.6 ACE Workshops and Management/Staff Travel | 17877.97 | 25000 | 7122.03 | 137282.29 | 127700 | -9582.29
3.7 Workshops/Serminars - Short Courses | 32123.49 | 55000 | 22876.51 | 461043.63 | 420000 | -41043.63
Sub Total | 96301.24 | 345000 | 248698.76 | 798959.31 | 1559420 | 760460.69 | Note 2 | 4 Years
4.0 Strengthen research capacity (excellence)
4.1 WACCI model farm upgrade | 26255.99 | 50000 | 23744.01 | 501263.87 | 450000 | -51263.87
4.2 New Lecture Rooms, Seed Science Laboratory and Bioinformatics Platform | 22434.88 | 225000 | 202565.12 | 2345414.9 | 2000000 | -345414.9
4.3 Students' supervisory committees and research supervision | 0 | 1250 | 1250 | 0 | 63350 | 63350
4.4 4 X 4 cross country SUV for research supervision | 0 | 0 |  | 115350.83 | 100042 | -15308.83
4.5 Peer-reviewed journals and publication | 1000 | 4500 | 3500 | 2735.81 | 26000 | 23264.19
4.6 Students' research | 89198.26 | 213324.8 | 124126.54 | 872551.34 | 1174812 | 302260.66
4.7 Seed Science Laboratory Equipment | 888.72 | 0 | -888.72 | 232309.08 | 232000 | -309.08
4.8 Bioinformatics Equipment & Accessories | 0 | 0 | 0 | 317970.76 | 295000 | -22970.76
4.9 Conference/Meeting room Equipment | 0 | 0 | 0 | 0 | 90000 | 90000
4.10 Tissue Culture/Cold room Equipment & Accessories | 11165.41 | 22000 | 10834.59 | 0 | 103835 | 103835
4.11 33-seator bus students' travel | 0 | 0 | 0 | 87704.64 | 93042 | 5337.36
4.12 Accounting database and maintenance | 4977.35 | 5500 | 522.65 | 15694.03 | 11000 | -4694.03
4.13 Network Equipment & Accessories | 0 | 0 | 0 | 11847.11 | 21000 | 9152.89
4.14 Computers and Accessories | 384.49 | 0 | -384.49 | 25817.44 | 25000 | -817.44
4.15 General Office Consumables | 1739.85 | 6000 | 4260.15 | 63788.43 | 55000 | -8788.43
4.15 Lecture Room Equipment & Accessories |  | 0 | 0 | 5108.73 | 6500 | 1391.27
4.16 Vehicle Running Costs | 18723.53 | 19000 | 276.47 | 95779.2 | 96000 | 220.8
4.17 Office Furniture & Fittings | 7704.91 | 2500 | -5204.91 | 67117.78 | 65000 | -2117.78
4.18 Students' Accommodation | 68863.7 | 0 | -68863.7 | 209864.58 | 201000 | -8864.58
4.19 Medical Insurance & Aid | 0 | 0 | 0 | 3952.98 | 4500 | 547.02
Sub Total | 253337.09 | 549074.8 | 295737.71 | 4974271.51 | 5113081 | 138809.49 | Note 2 | 4 Years
5.0 Strengthen education and research capacity (financial sustainability)
5.1 Raise revenue from external sources (full cost fees payment - Sponsors & Donors) |  | 0 | 0 | 0 | 0 | 0
5.2 Raise revenue from external sources (commercialization and tech. marketing) |  |  |  |  | 0
5.3 Raise revenue from external sources (short term training) |  |  |  |  | 0
5.4 Raise revenue from external sources (consultancy services) |  |  |  |  | 0
5.5 Raise revenue from external sources (fees from greenhouse facilities & labs) |  |  |  |  | 0
5.6 Raise revenue from external sources (rent from facilities hiring) |  |  |  |  | 0
5.7 Raise revenue from external sources (endowment funds establishment) |  |  |  |  | 0
5.8 Raise revenue from external sources (contract research overheads) |  |  |  |  | 0
0
Sub Total | 0 | 0 | 0 | 0 | 0 | 0
6.0 Strengthen education and research capacity
6.1 Provide and maintain academic infrastructure/T & R facilities | 169238.42 | 7500 | -161738.42 | 201128.54 | 71120.29 | -130008.25
Sub Total | 169238.42 | 7500 | -161738.42 | 201128.54 | 71120.29 | -130008.25 | Note 2
7.0 Adhere to best Financial Management Practices
7.1 Prepare and submit annual financial reports |  | 0 | 0 | 0 | 0 | 0
7.2 Ensure transparency in financial management (web-access to reports) |  | 0 | 0 | 0 | 0 | 0
7.3 Ensure internal & external audit oversight | 4746.85 | 16000 | 11253.15 | 41254.07 | 55000 | 13745.93
7.4 Ensure complete retirement of funds advanced for students' research |  | 0 | 0 | 0 | 0 | 0
Sub Total | 4746.85 | 16000 | 11253.15 | 41254.07 | 55000 | 13745.93
8.0 Undertake best procurement practices
8.1 Undertake third-party procurement processes verification | 10025.2 | 16000 | 5974.8 | 13464.98 | 31000 | 17535.02
8.1 Ensure timeliness of procurement process | 0 | 0 | 0 |  | 0 | 0
Sub Total | 10025.2 | 16000 | 5974.8 | 13464.98 | 31000 | 17535.02
Gain/Loss on Revaluation |  |  |  | -42943.27
Contingency | 1864.31 | 6000 | 4135.69 | 21005.45 | 100000 | 78994.55 | Note 3
Grand Total Uses of Funds | 679454.05 | 1199574.8 | 520120.75 | 7014975.57 | 8548321.29 | 1488902.45
Signed by:………………………
Prof. Eric Danquah
(Centre Leader)
Highlights for DLR 2.8
DLR 2.8.1 - New building construction | 0
DLR 2.8.2 - Laboratory equipment
DLR 2.8.3 - WACCI farm upgrade
DLR 2.8.4 - New building completion

## notes
AFRICA CENTER OF EXCELLENCE FOR TRAINING SEED SCIENTISTS & TECHNOLOGISTS
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED | AMOUNT DISBURSED | UNDISBURSED BALANCE
1.0 Set-up Institutional Framework for Commencement of Ace

## Sheet2
Desription | Amount (USD) | % of Award (USD)
Grant Budget (Award) | 8000000 | 100%
Cumulative Disbursement | 6600062.56 | 82.5%
Cumulative Expenditure | 7014975.57 | 87.69%